## Budget
JISC HE in FE Project Plan
Budget Analysis
1. Staffing | Salary (inc oncosts) | Proportion | Duration | Total | Actual Spend to Dec 08 | Projected Spend to Mar 08 | Comments
Project Manager | 55000 | 0.2 | 2 | 22846 | 16693 | 3200 | Spend only relates to Jan '08 onward. The costs from April '07 to Dec '07 are missing.
6538
Educational Technologist (mobile technology) | 30000 | 0.2 | 1.6 | 8867 | 5532 | 0 | Fatma left project in September 08
Educational Technologist (instructional design) | 30000 | 0.5 | 1.6 | 28122
Web Programmer | 30000 | 0.1 | 1.6 | 4800 | 33032.41 | 6711 | Query: more eTutor costs to be claimed from SMU?
Administration | 12000 | 0.1 | 1.5 | 1800 | 0 | 1800 | LCSS admin costs to be recharged to the project
On-line Tutor Costs | 1000 | 10 | 1 | 10000 | 0 | 6000 | To be claimed from Bridgend, Merthyr & Swansea colleges
Learner Costs | 50 | 60 | 1.5 | 3500 | 0 | 1500 | To be claimed from Bridgend, Merthyr & Swansea colleges
Travel & Subsistence | 5150 | 1 | 1.5 | 5500 | 2616.4 | 500 | No costs claimed by partner colleges to date.
2. Non Staffing
Equipment | 4000 |  |  | 3000 | 900 | 0
Consumables | 3000 |  |  | 3000 | 1569.35 | 300
Evaluation/Dissemination | 3000 |  |  | 3000 | 0 | 3000 | Dissemination conference on 3rd April
CSO Administration | 2000 |  |  | 2000 | 0 | 2000 | Query: institutional admin costs to be included/recharged?
Total |  |  |  | 96435 | 60343.16 | 91892.16
remaining budget: |  |  |  |  | 36091.84 | 4542.84

## Cash Flow
JISC HE in FE Project: WALES
Budget and Cash Flow
1. Staffing | Budget | Cash Flow | 2007-04-01 | 2007-05-01 | 2007-06-01 | 2007-07-01 | 2007-08-01 | 2007-09-01 | 2007-10-01 | 2007-11-01 | 2007-12-01 | 2008-01-01 | 2008-02-01 | 2008-03-01 | 2008-04-01 | 2008-05-01 | 2008-06-01 | 2008-07-01 | 2008-08-01 | 2008-09-01 | 2008-10-01 | 2008-11-01 | 2008-12-01 | 2009-01-01 | 2009-02-01 | 2009-03-01
Directly Incurred
Project Manager | 22846 | 27494.25 | 964.25 | 964.25 | 964.25 | 964.25 | 964.25 | 964.25 | 964.25 | 0 | 0 | 1669.5 | 1445.5 | 1477 | 1253 | 962.5 | 1501.5 | 1428 | 1011.5 | 1428 | 1428 | 1428 | 1428 | 1428 | 1428 | 1428
Educational Technologist | 8867 | 8293.297 | 340.467 | 340.467 | 340.467 | 340.467 | 340.467 | 340.467 | 340.467 | 340.467 | 340.467 | 340.467 | 340.467 | 340 | 350.68 | 350.68 | 350.68 | 350.68 | 350.68 | 350.68 | 350.68 | 350.68 | 350.68 | 350.68 | 350.68 | 350.68
(mobile technology)
Educational Technologist | 28122 | 28704 | 0 | 0 | 0 | 0 | 1410 | 1410 | 1410 | 1410 | 1410 | 1410 | 1410 | 1410 | 1452 | 1452 | 1452 | 1452 | 1452 | 1452 | 1452 | 1452 | 1452 | 1452 | 1452 | 1452
(social software)
Web Programmer | 4800 | 7455 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 392 | 392 | 392 | 392 | 392 | 785 | 785 | 785 | 785 | 785 | 785 | 785
Administration | 1800 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
On-line Tutor Costs | 10000 | 10000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6000 | 0 | 0 | 0 | 4000 | 0
Learner Costs | 4500 | 4500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2500 | 0 | 0 | 0 | 2000 | 0
Travel & Subsistence | 5500 | 4392.7 | 0 | 96.45 | 113.65 | 112.65 | 36.65 | 50 | 219.65 | 0 | 0 | 160 | 207.6 | 268.55 | 413.3 | 136 | 244.4 | 202.6 | 131.2 | 0 | 500 | 0 | 0 | 1000 | 0 | 500
Directly Allocated
Administration Costs | 2000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Sub-total: staffing | 88435 | 90839.247 | 1304.717 | 1401.167 | 1418.367 | 1417.367 | 2751.367 | 2764.717 | 2934.367 | 1750.467 | 1750.467 | 3579.967 | 3403.567 | 3495.55 | 3860.98 | 3293.18 | 3940.58 | 3825.28 | 3337.38 | 4015.68 | 13015.68 | 4015.68 | 4015.68 | 5015.68 | 10015.68 | 4515.68
2. Non Staffing
Equipment | 2500 | 1000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1000 | 0 | 0 | 0 | 0 | 0
Consumables | 2500 | 1733.64 | 0 | 0 | 0 | 0 | 0 | 0 | 500 | 0 | 0 | 0 | 0 | 233.64 | 0 | 0 | 0 | 0 | 0 | 0 | 500 | 0 | 0 | 500 | 0 | 0
Evaluation/Dissemination | 3000 | 1500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 500 | 0 | 1000
Sub-total: non-staffing | 8000 | 4233.64 | 0 | 0 | 0 | 0 | 0 | 0 | 500 | 0 | 0 | 0 | 0 | 233.64 | 0 | 0 | 0 | 0 | 0 | 0 | 1500 | 0 | 0 | 1000 | 0 | 1000
Total | 96435 | 95072.887 | 1304.717 | 1401.167 | 1418.367 | 1417.367 | 2751.367 | 2764.717 | 3434.367 | 1750.467 | 1750.467 | 3579.967 | 3403.567 | 3729.19 | 3860.98 | 3293.18 | 3940.58 | 3825.28 | 3337.38 | 4015.68 | 14515.68 | 4015.68 | 4015.68 | 6015.68 | 10015.68 | 5515.68

## Workplan
JISC HE in FE Project Proposal
Workplan
Year | 2007 | [9 empty] | 2008 | [11 empty] | 2009
Month | Mar | Apr | May | Jun | Jul | Aug | Sep | Oct | Nov | Dec | Jan | Feb | Mar | Apr | May | Jun | Jul | Aug | Sep | Oct | Nov | Dec | Jan | Feb | Mar
Activity
Staffing
Manager
Technologist (M)
Technologist (ID)
Web Programmer
Administrator
Tutors
Activities
Project Setup
Initial Evaluation
Social Software Plan
Mobile Technology Plan
Software/Hardware Procurement
Installation and Testing
Learner Support Planning
Tutor Training
Learner Training
Learner Support
Learner Evaluation
Tutor Evaluation